UNDERTAKING A PROJECT – THE FEASIBILITY STUDY

Ellie Bouchan and Simon Fox

East Norfolk Multi Academy Trust

Contents

what is a feasibility study?	2

Industry Support	2

Specific Activities Undertaken	3

The brief	3

Research and Development	3

Questionnaires	3

Workshop	4

Specific, allocated tasks	4

# what is a feasibility study?

A feasibility study is a structured approach that analyses whether or not a proposed project is logistically possible.

In 2020, East Norfolk Sixth Form College started working in partnership with Great Yarmouth Borough Council, Here Studio and the Preservation Trust to develop a feasibility study for a locally relevant video game. The video game ties into a large-scale project, focusing on history and mapping.

This guide is designed to give you an idea of how to run a feasibility study. The guide will take you through the steps involved in our ‘live’ project. It should also demonstrate that there is a plethora of roles and progression routes for young people taking digital technology-based subjects and that not everyone needs to be a top-class programmer to succeed in the industry.

We would advise anyone who reads this guide to conduct some research into IT-based careers so you can see the sheer amount available.

The following sites are really useful for those looking to gain an understanding of the progression routes:

- Prospects: https://www.prospects.ac.uk/jobs-and-work-experience/job-sectors/information-technology/overview-of-the-uks-it-industry

- National Careers Service: https://nationalcareers.service.gov.uk/job-categories/computing-technology-and-digital

- The Chartered Institute for IT: https://www.bcs.org/

|  | # Industry Support Lou Robson, Heritage Action Zone project manager at Great Yarmouth Borough Council says: “Working with students who live in the area has been brilliant. They’ve brought new ideas and understanding to a real-life project and we’ve shown them you can explore digital careers in the heritage sector too!’’ # Specific Activities Undertaken This is how we got the project started: ## The brief Lou Robson generated a brief and contacted potential partners. This is an extract from the initial planning document that can be used to secure funding (if needed) and to engage project partners: Great Yarmouth Borough Council is seeking to commission a team of game-design specialists to develop a feasibility study for an immersive history-based game that will encourage people to explore the historic centre of the town. The project will align with plans to develop a wider interactive digital mapping resource and a knowledge-sharing platform, with geo-referenced maps, photographs, and information about the High Streets Heritage Action Zone area. The team will comprise a partnership of educators from East Norfolk College and independent professionals Here Design, with potential for involvement of Norwich University of Arts and East Norfolk students. The lead for the project will be East Norfolk College. The team will be responsible for developing a proposal for a game that acts as a gateway to exploring the history of Great Yarmouth. It will also serve as an ‘onboarding’ tool to engage users with the digital mapping platform. Developing employable and enjoyable skills through involvement in projects from start to finish is a principle of the Great Yarmouth scheme as is partnership-working with cultural, educational, business and heritage organisations in the borough. By the end of the project, a comprehensive feasibility study will be completed, with strategies for future development and implementation outlined. ## Research and Development ### Questionnaires After some initial discussions between the agreed partners regarding what they felt needed to be included and considered (intended audience, platforms, accessibility etc.), East Norfolk and Here Studios created a questionnaire based on ideas generated during the meetings. These questionnaires were then distributed electronically as they had been created using Google Forms. They were then initially sent to subject-relevant students (who were taking Games and Esports-related qualifications) and then distributed more widely to the rest of the cohort. Distributing the questionnaire in this manner allowed for a comparison between responses of those that likely play games more regularly and those who don’t and ensured that respondents were in the primary demographic profile for the product. Results allowed for solidification of some initial ideas and raised some further areas for investigation. ## Workshop To further explore particular elements of the project and certain areas of interest highlighted by the survey results, all parties coordinated a workshop at East Norfolk to get young people more directly involved by conducting some enhanced quantitative and qualitative research. The Heritage Action Zone Project Manager, Here Studios and The Preservation Trust worked together to create a series of talks and activities which were delivered to a cohort of around 60 Games students. The day involved a project overview from The Preservation Trust and Heritage Action Zone, followed by a series of group-based activities which required students to generate, share and feedback ideas. East Norfolk provided the space, resources and refreshments and the staff to facilitate the safe working environment. Students were given visual materials prepared by the speakers and those delivering the workshop. Large sheets of paper lined the tables so that all students were encouraged to participate at all times during the workshop. The workshop was a great opportunity to further consolidate ideas and also afforded an opportunity to generate visual materials and evidence for stakeholders invested in the project. # Specific, allocated tasks Depending on a person’s role, experience and / or expertise, they can be allocated a specific task. Next steps The next step is to put the findings into a formal document, which will be the feasibility study. This document should be detailed and led by the research and development that was undertaken throughout the initial stages of the project. It is a collaborative document and all parties can be invited to have input. The feasibility study document itself will contain evidence-driven detail for the key stages detailed above (or whichever stages you outline for your project). For example, this could contain results from surveys and questionnaires, summaries of outcomes from workshops and responses from individual allocated tasks, such as researching and confirming legal requirements. These documents can be quite lengthy, but if you are lucky enough to secure funding for a project, the additional details are often essential for evidencing value for money and they can be reused and shared internally or with other organisations to start more projects, which can be of enormous benefit. |
| --- | --- |

THANK YOU

Our Partners							Funded by